## Work Items
Work Item ID | Work Item | Department | Assigned To | Opened Date | Target Date | Task Duration (days) | Progress Status | Overdue Flag | Latest Note
MKT-26-0001 | Phase 2: coordinate creative asset review | Marketing | Ethan Brooks | 2026-10-14 | 2026-10-24 |  | Not Started |  | Scheduled for the next planning session.
OPS-26-0002 | Customer: review warehouse picking workflow | Operations | Sophie Taylor | 2026-11-25 | 2026-11-30 |  | In Progress |  | Draft prepared and awaiting feedback.
TEC-26-0003 | Phase 2: update application support notes | Technology | Noah Williams | 2026-09-04 | 2026-09-06 |  | In Progress |  | Initial review is complete.
FIN-26-0004 | FY27: update cash flow assumptions | Finance | Mia Nguyen | 2026-10-29 | 2026-11-19 |  | In Progress |  | A few items still need confirmation.
MKT-26-0005 | FY27: coordinate creative asset review | Marketing | Ethan Brooks | 2026-09-26 | 2026-10-07 |  | In Progress |  | Draft prepared and awaiting feedback.
OPS-26-0006 | Customer: coordinate regional delivery schedule | Operations | Oliver Chen | 2026-10-28 | 2026-11-01 |  | On Hold |  | Waiting for revised requirements.
PPL-26-0007 | Monthly: update workplace policy guide | People & Culture | Lucas Brown | 2026-10-11 | 2026-10-27 |  | Completed |  | Final version has been circulated.
OPS-26-0008 | Internal: update stock replenishment guide | Operations | Noah Williams | 2026-09-30 | 2026-10-02 |  | Completed |  | Closed after team review.
STR-26-0009 | Monthly: review project milestone risks | Strategy | Ethan Brooks | 2026-10-09 | 2026-10-20 |  | In Progress |  | Initial review is complete.
CX-26-0010 | Customer: review service quality sample | Customer Experience | Ava Thompson | 2026-10-17 | 2026-11-01 |  | In Progress |  | Work is underway; next update is due shortly.
OPS-26-0011 | Monthly: prepare weekly fulfilment summary | Operations | Jack Patel | 2026-11-01 | 2026-11-05 |  | In Progress |  | A few items still need confirmation.
TEC-26-0012 | Customer: prepare user acceptance test cases | Technology | Mia Nguyen | 2026-11-11 | 2026-11-21 |  | Completed |  | Deliverable accepted by the relevant lead.
MKT-26-0013 | Customer: review campaign performance | Marketing | Jack Patel | 2026-11-17 | 2026-11-30 |  | Completed |  | Final version has been circulated.
TEC-26-0014 | Phase 2: test reporting dashboard filters | Technology | Mia Nguyen | 2026-11-02 | 2026-11-07 |  | In Progress |  | A few items still need confirmation.
MKT-26-0015 | Coordinate creative asset review | Marketing | Ava Thompson | 2026-10-22 | 2026-10-30 |  | In Progress |  | Draft prepared and awaiting feedback.
OPS-26-0016 | Internal: reorganise storage location labels | Operations | Oliver Chen | 2026-09-05 | 2026-09-21 |  | In Progress |  | Draft prepared and awaiting feedback.
MKT-26-0017 | Monthly: plan seasonal promotion | Marketing | Oliver Chen | 2026-09-28 | 2026-10-03 |  | In Progress |  | Follow-up with stakeholders is planned.
PPL-26-0018 | Monthly: collect induction feedback | People & Culture | Lucas Brown | 2026-09-07 | 2026-09-30 |  | In Progress |  | Initial review is complete.
PPL-26-0019 | Customer: prepare recruitment shortlist | People & Culture | Sophie Taylor | 2026-10-03 | 2026-10-05 |  | On Hold |  | Paused pending a decision from the project lead.
MKT-26-0020 | Coordinate creative asset review | Marketing | Priya Shah | 2026-10-10 | 2026-10-22 |  | Completed |  | Deliverable accepted by the relevant lead.
PPL-26-0021 | Internal: collect induction feedback | People & Culture | Sophie Taylor | 2026-11-01 | 2026-11-16 |  | Completed |  | Final version has been circulated.
TEC-26-0022 | FY27: resolve spreadsheet validation issues | Technology | Oliver Chen | 2026-11-19 | 2026-11-30 |  | Not Started |  | Owner to confirm the first milestone.
TEC-26-0023 | Customer: document database refresh process | Technology | Amelia Wilson | 2026-11-09 | 2026-11-13 |  | In Progress |  | Follow-up with stakeholders is planned.
STR-26-0024 | Monthly: summarise stakeholder workshop findings | Strategy | Ethan Brooks | 2026-11-04 | 2026-11-26 |  | In Progress |  | A few items still need confirmation.
FIN-26-0025 | Phase 2: refresh department budget tracker | Finance | Amelia Wilson | 2026-10-23 | 2026-10-29 |  | Completed |  | Deliverable accepted by the relevant lead.
TEC-26-0026 | FY27: update system change log | Technology | Oliver Chen | 2026-10-01 | 2026-10-19 |  | Completed |  | Reviewed and saved in the shared workspace.
FIN-26-0027 | Internal: refresh department budget tracker | Finance | Amelia Wilson | 2026-11-16 | 2026-11-23 |  | Completed |  | Deliverable accepted by the relevant lead.
OPS-26-0028 | FY27: improve returns processing steps | Operations | Jack Patel | 2026-09-23 | 2026-10-03 |  | On Hold |  | Paused pending a decision from the project lead.
TEC-26-0029 | Internal: update system change log | Technology | Ethan Brooks | 2026-09-14 | 2026-10-04 |  | In Progress |  | Initial review is complete.
OPS-26-0030 | Monthly: review warehouse picking workflow | Operations | Oliver Chen | 2026-09-28 | 2026-10-06 |  | Completed |  | Final version has been circulated.
OPS-26-0031 | Monthly: improve returns processing steps | Operations | Ethan Brooks | 2026-10-28 | 2026-11-19 |  | Completed |  | Deliverable accepted by the relevant lead.
TEC-26-0032 | FY27: resolve spreadsheet validation issues | Technology | Ethan Brooks | 2026-09-12 | 2026-09-30 |  | In Progress |  | Draft prepared and awaiting feedback.
FIN-26-0033 | FY27: check recurring software charges | Finance | Amelia Wilson | 2026-10-24 | 2026-11-16 |  | On Hold |  | Waiting for revised requirements.
STR-26-0034 | Customer: summarise stakeholder workshop findings | Strategy | Lucas Brown | 2026-11-04 | 2026-11-16 |  | Completed |  | Final version has been circulated.
PPL-26-0035 | Organise internal learning session | People & Culture | Isabella Martin | 2026-09-26 | 2026-10-16 |  | Completed |  | Final version has been circulated.
FIN-26-0036 | Customer: confirm outstanding payment list | Finance | Isabella Martin | 2026-09-07 | 2026-09-18 |  | In Progress |  | Progress is being tracked in the team register.
STR-26-0037 | Monthly: compile market trend summary | Strategy | Priya Shah | 2026-10-07 | 2026-10-22 |  | Completed |  | Closed after team review.
PPL-26-0038 | Regional: collect induction feedback | People & Culture | Sophie Taylor | 2026-09-03 | 2026-09-20 |  | In Progress |  | Work is underway; next update is due shortly.
STR-26-0039 | Monthly: review project milestone risks | Strategy | Mia Nguyen | 2026-11-05 | 2026-11-26 |  | On Hold |  | Resourcing needs to be confirmed.
OPS-26-0040 | Phase 2: audit order dispatch records | Operations | Amelia Wilson | 2026-11-02 | 2026-11-04 |  | Completed |  | Deliverable accepted by the relevant lead.
PPL-26-0041 | Regional: refresh staff training register | People & Culture | Priya Shah | 2026-09-07 | 2026-09-26 |  | Completed |  | Checks completed; no major issues found.
MKT-26-0042 | FY27: build customer email calendar | Marketing | Mia Nguyen | 2026-09-24 | 2026-10-07 |  | Completed |  | Final version has been circulated.
MKT-26-0043 | Internal: review search advertising results | Marketing | Mia Nguyen | 2026-10-08 | 2026-10-26 |  | In Progress |  | Progress is being tracked in the team register.
CX-26-0044 | Customer: identify repeat contact drivers | Customer Experience | Jack Patel | 2026-10-25 | 2026-11-07 |  | In Progress |  | A few items still need confirmation.
TEC-26-0045 | FY27: check automated report schedule | Technology | Ethan Brooks | 2026-11-09 | 2026-11-11 |  | Not Started |  | Scheduled for the next planning session.
OPS-26-0046 | Monthly: coordinate regional delivery schedule | Operations | Noah Williams | 2026-09-24 | 2026-10-01 |  | On Hold |  | Paused pending a decision from the project lead.
CX-26-0047 | FY27: analyse customer satisfaction results | Customer Experience | Noah Williams | 2026-11-07 | 2026-11-09 |  | Not Started |  | Waiting for the initial briefing.
TEC-26-0048 | Internal: prepare user acceptance test cases | Technology | Ethan Brooks | 2026-10-20 | 2026-11-07 |  | In Progress |  | Draft prepared and awaiting feedback.
FIN-26-0049 | Internal: check recurring software charges | Finance | Liam Carter | 2026-10-22 | 2026-10-28 |  | Not Started |  | Dependencies are being checked.
TEC-26-0050 | Customer: test reporting dashboard filters | Technology | Isabella Martin | 2026-09-12 | 2026-09-22 |  | In Progress |  | Draft prepared and awaiting feedback.
MKT-26-0051 | Internal: coordinate creative asset review | Marketing | Jack Patel | 2026-09-14 | 2026-09-19 |  | Not Started |  | Owner to confirm the first milestone.
STR-26-0052 | Monthly: prepare leadership briefing notes | Strategy | Liam Carter | 2026-10-07 | 2026-10-21 |  | Not Started |  | Owner to confirm the first milestone.
MKT-26-0053 | Regional: review search advertising results | Marketing | Oliver Chen | 2026-11-18 | 2026-11-30 |  | In Progress |  | Follow-up with stakeholders is planned.
TEC-26-0054 | Monthly: resolve spreadsheet validation issues | Technology | Amelia Wilson | 2026-09-30 | 2026-10-15 |  | In Progress |  | Progress is being tracked in the team register.
STR-26-0055 | Customer: update annual planning assumptions | Strategy | Jack Patel | 2026-09-02 | 2026-09-23 |  | In Progress |  | Follow-up with stakeholders is planned.
FIN-26-0056 | Internal: check recurring software charges | Finance | Amelia Wilson | 2026-09-27 | 2026-10-01 |  | Completed |  | Closed after team review.
TEC-26-0057 | Customer: clean customer data extract | Technology | Oliver Chen | 2026-10-02 | 2026-10-15 |  | In Progress |  | Draft prepared and awaiting feedback.
MKT-26-0058 | Phase 2: analyse social engagement trends | Marketing | Ethan Brooks | 2026-09-28 | 2026-10-01 |  | Not Started |  | Dependencies are being checked.
FIN-26-0059 | Customer: review project expenditure | Finance | Lucas Brown | 2026-09-12 | 2026-09-26 |  | Completed |  | Reviewed and saved in the shared workspace.
OPS-26-0060 | Phase 2: reorganise storage location labels | Operations | Ava Thompson | 2026-10-06 | 2026-10-24 |  | Not Started |  | Dependencies are being checked.
PPL-26-0061 | Phase 2: coordinate team feedback survey | People & Culture | Ava Thompson | 2026-09-03 | 2026-09-08 |  | In Progress |  | Work is underway; next update is due shortly.
STR-26-0062 | Internal: prepare leadership briefing notes | Strategy | Oliver Chen | 2026-11-21 | 2026-11-24 |  | In Progress |  | Draft prepared and awaiting feedback.
TEC-26-0063 | Regional: update application support notes | Technology | Amelia Wilson | 2026-10-13 | 2026-10-24 |  | Completed |  | Closed after team review.
CX-26-0064 | Regional: review customer complaint themes | Customer Experience | Amelia Wilson | 2026-10-14 | 2026-10-22 |  | In Progress |  | Follow-up with stakeholders is planned.
PPL-26-0065 | Monthly: schedule onboarding sessions | People & Culture | Liam Carter | 2026-10-20 | 2026-10-25 |  | On Hold |  | Resourcing needs to be confirmed.
STR-26-0066 | Internal: update annual planning assumptions | Strategy | Sophie Taylor | 2026-09-10 | 2026-10-03 |  | Completed |  | Reviewed and saved in the shared workspace.
STR-26-0067 | Internal: summarise stakeholder workshop findings | Strategy | Ethan Brooks | 2026-11-05 | 2026-11-12 |  | Completed |  | Deliverable accepted by the relevant lead.
PPL-26-0068 | Prepare recruitment shortlist | People & Culture | Sophie Taylor | 2026-11-25 | 2026-11-30 |  | Completed |  | Deliverable accepted by the relevant lead.
CX-26-0069 | FY27: prepare customer feedback summary | Customer Experience | Liam Carter | 2026-11-20 | 2026-11-30 |  | Not Started |  | Waiting for the initial briefing.
TEC-26-0070 | Customer: prepare user acceptance test cases | Technology | Priya Shah | 2026-10-16 | 2026-11-03 |  | Not Started |  | Owner to confirm the first milestone.
TEC-26-0071 | Regional: review backup status | Technology | Isabella Martin | 2026-11-17 | 2026-11-23 |  | Completed |  | Reviewed and saved in the shared workspace.
PPL-26-0072 | Phase 2: prepare recruitment shortlist | People & Culture | Oliver Chen | 2026-09-22 | 2026-10-07 |  | Not Started |  | Owner to confirm the first milestone.
OPS-26-0073 | Monthly: coordinate regional delivery schedule | Operations | Amelia Wilson | 2026-10-16 | 2026-10-20 |  | Completed |  | Closed after team review.
MKT-26-0074 | Prepare product launch brief | Marketing | Priya Shah | 2026-09-28 | 2026-10-18 |  | Completed |  | Reviewed and saved in the shared workspace.
STR-26-0075 | Regional: compile market trend summary | Strategy | Ethan Brooks | 2026-10-12 | 2026-10-24 |  | Completed |  | Final version has been circulated.
CX-26-0076 | Internal: check unresolved support requests | Customer Experience | Priya Shah | 2026-09-01 | 2026-09-19 |  | In Progress |  | Follow-up with stakeholders is planned.
CX-26-0077 | Customer: review service quality sample | Customer Experience | Noah Williams | 2026-09-15 | 2026-10-01 |  | On Hold |  | Paused pending a decision from the project lead.
OPS-26-0078 | Improve returns processing steps | Operations | Ava Thompson | 2026-10-03 | 2026-10-22 |  | In Progress |  | A few items still need confirmation.
MKT-26-0079 | Phase 2: refresh campaign tracking sheet | Marketing | Isabella Martin | 2026-09-02 | 2026-09-21 |  | On Hold |  | Paused pending a decision from the project lead.
MKT-26-0080 | Internal: refresh campaign tracking sheet | Marketing | Priya Shah | 2026-11-08 | 2026-11-24 |  | Not Started |  | Dependencies are being checked.
FIN-26-0081 | Phase 2: check recurring software charges | Finance | Noah Williams | 2026-11-11 | 2026-11-27 |  | In Progress |  | A few items still need confirmation.
MKT-26-0082 | Monthly: prepare product launch brief | Marketing | Jack Patel | 2026-11-10 | 2026-11-15 |  | Not Started |  | Dependencies are being checked.
TEC-26-0083 | Test reporting dashboard filters | Technology | Ethan Brooks | 2026-09-24 | 2026-10-14 |  | In Progress |  | Initial review is complete.
PPL-26-0084 | FY27: review leave coverage plan | People & Culture | Sophie Taylor | 2026-09-06 | 2026-09-10 |  | Not Started |  | Waiting for the initial briefing.
MKT-26-0085 | Internal: update website product copy | Marketing | Amelia Wilson | 2026-11-02 | 2026-11-05 |  | In Progress |  | Work is underway; next update is due shortly.
OPS-26-0086 | Regional: reorganise storage location labels | Operations | Isabella Martin | 2026-09-22 | 2026-10-09 |  | In Progress |  | Work is underway; next update is due shortly.
MKT-26-0087 | Regional: review search advertising results | Marketing | Mia Nguyen | 2026-09-20 | 2026-09-24 |  | In Progress |  | Draft prepared and awaiting feedback.
FIN-26-0088 | Regional: refresh department budget tracker | Finance | Ethan Brooks | 2026-11-23 | 2026-11-27 |  | On Hold |  | Resourcing needs to be confirmed.
CX-26-0089 | Internal: review customer complaint themes | Customer Experience | Amelia Wilson | 2026-09-11 | 2026-09-19 |  | Not Started |  | Dependencies are being checked.
STR-26-0090 | Monthly: review process improvement proposals | Strategy | Mia Nguyen | 2026-09-30 | 2026-10-19 |  | Not Started |  | Scheduled for the next planning session.
TEC-26-0091 | Monthly: review access permissions | Technology | Liam Carter | 2026-11-14 | 2026-11-22 |  | Not Started |  | Dependencies are being checked.
PPL-26-0092 | Internal: refresh staff training register | People & Culture | Liam Carter | 2026-10-24 | 2026-11-09 |  | Completed |  | Deliverable accepted by the relevant lead.
STR-26-0093 | Internal: review project milestone risks | Strategy | Oliver Chen | 2026-10-04 | 2026-10-21 |  | Completed |  | Closed after team review.
TEC-26-0094 | FY27: review access permissions | Technology | Isabella Martin | 2026-11-15 | 2026-11-17 |  | Completed |  | Reviewed and saved in the shared workspace.
PPL-26-0095 | Customer: coordinate team feedback survey | People & Culture | Mia Nguyen | 2026-09-21 | 2026-10-01 |  | In Progress |  | Draft prepared and awaiting feedback.
CX-26-0096 | FY27: check unresolved support requests | Customer Experience | Isabella Martin | 2026-11-23 | 2026-11-30 |  | In Progress |  | Progress is being tracked in the team register.
PPL-26-0097 | Customer: review leave coverage plan | People & Culture | Sophie Taylor | 2026-10-03 | 2026-10-17 |  | Completed |  | Final version has been circulated.
TEC-26-0098 | Monthly: test reporting dashboard filters | Technology | Ethan Brooks | 2026-11-13 | 2026-11-30 |  | In Progress |  | A few items still need confirmation.
MKT-26-0099 | Internal: review campaign performance | Marketing | Noah Williams | 2026-11-22 | 2026-11-26 |  | In Progress |  | Follow-up with stakeholders is planned.
PPL-26-0100 | Customer: update workplace policy guide | People & Culture | Priya Shah | 2026-10-16 | 2026-10-30 |  | In Progress |  | Follow-up with stakeholders is planned.
STR-26-0101 | FY27: update annual planning assumptions | Strategy | Sophie Taylor | 2026-10-15 | 2026-10-18 |  | In Progress |  | Draft prepared and awaiting feedback.
TEC-26-0102 | Phase 2: review backup status | Technology | Ava Thompson | 2026-10-02 | 2026-10-21 |  | In Progress |  | Progress is being tracked in the team register.
CX-26-0103 | Phase 2: refresh help centre articles | Customer Experience | Liam Carter | 2026-10-05 | 2026-10-22 |  | In Progress |  | Follow-up with stakeholders is planned.
CX-26-0104 | Identify repeat contact drivers | Customer Experience | Liam Carter | 2026-10-25 | 2026-11-13 |  | Completed |  | Deliverable accepted by the relevant lead.
STR-26-0105 | Monthly: update annual planning assumptions | Strategy | Amelia Wilson | 2026-10-28 | 2026-11-20 |  | Completed |  | Closed after team review.
CX-26-0106 | FY27: refresh help centre articles | Customer Experience | Liam Carter | 2026-11-04 | 2026-11-27 |  | In Progress |  | Draft prepared and awaiting feedback.
TEC-26-0107 | Internal: test reporting dashboard filters | Technology | Priya Shah | 2026-09-26 | 2026-10-04 |  | Completed |  | Final version has been circulated.
TEC-26-0108 | Regional: update application support notes | Technology | Mia Nguyen | 2026-09-06 | 2026-09-30 |  | In Progress |  | Work is underway; next update is due shortly.
STR-26-0109 | Customer: summarise stakeholder workshop findings | Strategy | Noah Williams | 2026-09-29 | 2026-10-13 |  | In Progress |  | Follow-up with stakeholders is planned.
MKT-26-0110 | Analyse social engagement trends | Marketing | Liam Carter | 2026-11-21 | 2026-11-30 |  | Completed |  | Final version has been circulated.
CX-26-0111 | Phase 2: refresh help centre articles | Customer Experience | Liam Carter | 2026-09-04 | 2026-09-24 |  | In Progress |  | Follow-up with stakeholders is planned.
STR-26-0112 | Internal: compare competitor service offers | Strategy | Sophie Taylor | 2026-11-09 | 2026-11-21 |  | Completed |  | Deliverable accepted by the relevant lead.
OPS-26-0113 | FY27: improve returns processing steps | Operations | Liam Carter | 2026-09-05 | 2026-09-28 |  | Completed |  | Final version has been circulated.
OPS-26-0114 | Regional: update stock replenishment guide | Operations | Jack Patel | 2026-09-26 | 2026-10-01 |  | On Hold |  | Waiting for revised requirements.
CX-26-0115 | Monthly: review service quality sample | Customer Experience | Ethan Brooks | 2026-09-12 | 2026-10-05 |  | Completed |  | Closed after team review.
OPS-26-0116 | Improve returns processing steps | Operations | Jack Patel | 2026-11-27 | 2026-11-30 |  | Not Started |  | Waiting for the initial briefing.
FIN-26-0117 | FY27: refresh department budget tracker | Finance | Priya Shah | 2026-10-22 | 2026-11-15 |  | Completed |  | Reviewed and saved in the shared workspace.
TEC-26-0118 | Internal: document database refresh process | Technology | Liam Carter | 2026-11-25 | 2026-11-30 |  | Not Started |  | Dependencies are being checked.
STR-26-0119 | Monthly: review project milestone risks | Strategy | Sophie Taylor | 2026-09-11 | 2026-09-13 |  | In Progress |  | Progress is being tracked in the team register.
OPS-26-0120 | Phase 2: coordinate regional delivery schedule | Operations | Oliver Chen | 2026-10-03 | 2026-10-17 |  | In Progress |  | Draft prepared and awaiting feedback.
STR-26-0121 | Regional: prepare leadership briefing notes | Strategy | Isabella Martin | 2026-11-08 | 2026-11-18 |  | Not Started |  | Scheduled for the next planning session.
TEC-26-0122 | Regional: review access permissions | Technology | Amelia Wilson | 2026-09-26 | 2026-10-02 |  | Not Started |  | Owner to confirm the first milestone.
CX-26-0123 | Internal: identify repeat contact drivers | Customer Experience | Noah Williams | 2026-11-19 | 2026-11-30 |  | In Progress |  | Follow-up with stakeholders is planned.
MKT-26-0124 | FY27: analyse social engagement trends | Marketing | Jack Patel | 2026-09-07 | 2026-09-10 |  | Completed |  | Final version has been circulated.
CX-26-0125 | Review customer complaint themes | Customer Experience | Amelia Wilson | 2026-10-18 | 2026-11-08 |  | Completed |  | Checks completed; no major issues found.
STR-26-0126 | Monthly: review process improvement proposals | Strategy | Isabella Martin | 2026-11-14 | 2026-11-30 |  | Not Started |  | Owner to confirm the first milestone.
OPS-26-0127 | Regional: reorganise storage location labels | Operations | Isabella Martin | 2026-11-08 | 2026-11-30 |  | On Hold |  | Waiting for revised requirements.
FIN-26-0128 | Customer: update cash flow assumptions | Finance | Liam Carter | 2026-09-04 | 2026-09-28 |  | In Progress |  | Follow-up with stakeholders is planned.
PPL-26-0129 | Monthly: check employee records | People & Culture | Isabella Martin | 2026-09-07 | 2026-09-13 |  | In Progress |  | Initial review is complete.
PPL-26-0130 | FY27: update workplace policy guide | People & Culture | Ethan Brooks | 2026-09-15 | 2026-09-22 |  | In Progress |  | A few items still need confirmation.
TEC-26-0131 | Regional: check automated report schedule | Technology | Isabella Martin | 2026-11-17 | 2026-11-30 |  | In Progress |  | A few items still need confirmation.
OPS-26-0132 | Internal: improve returns processing steps | Operations | Priya Shah | 2026-09-27 | 2026-10-11 |  | In Progress |  | Follow-up with stakeholders is planned.
PPL-26-0133 | FY27: update workplace policy guide | People & Culture | Priya Shah | 2026-10-22 | 2026-11-11 |  | Not Started |  | Waiting for the initial briefing.
MKT-26-0134 | Monthly: analyse social engagement trends | Marketing | Ethan Brooks | 2026-09-20 | 2026-09-29 |  | In Progress |  | Follow-up with stakeholders is planned.
MKT-26-0135 | Phase 2: build customer email calendar | Marketing | Isabella Martin | 2026-11-11 | 2026-11-30 |  | On Hold |  | Paused pending a decision from the project lead.
FIN-26-0136 | Update cash flow assumptions | Finance | Amelia Wilson | 2026-10-02 | 2026-10-06 |  | In Progress |  | Work is underway; next update is due shortly.
FIN-26-0137 | FY27: check recurring software charges | Finance | Mia Nguyen | 2026-09-22 | 2026-10-03 |  | Not Started |  | Dependencies are being checked.
MKT-26-0138 | Customer: review campaign performance | Marketing | Oliver Chen | 2026-11-11 | 2026-11-30 |  | In Progress |  | Follow-up with stakeholders is planned.
STR-26-0139 | Internal: review process improvement proposals | Strategy | Amelia Wilson | 2026-10-04 | 2026-10-10 |  | On Hold |  | Paused pending a decision from the project lead.
OPS-26-0140 | Customer: review warehouse picking workflow | Operations | Lucas Brown | 2026-11-08 | 2026-11-17 |  | Completed |  | Closed after team review.
MKT-26-0141 | Monthly: update website product copy | Marketing | Ava Thompson | 2026-09-13 | 2026-09-19 |  | Completed |  | Closed after team review.
OPS-26-0142 | Coordinate regional delivery schedule | Operations | Priya Shah | 2026-09-07 | 2026-09-20 |  | In Progress |  | Follow-up with stakeholders is planned.
FIN-26-0143 | Customer: check recurring software charges | Finance | Mia Nguyen | 2026-09-09 | 2026-09-28 |  | In Progress |  | Progress is being tracked in the team register.
FIN-26-0144 | Internal: review project expenditure | Finance | Ethan Brooks | 2026-09-14 | 2026-10-06 |  | On Hold |  | Waiting for revised requirements.
STR-26-0145 | Customer: update annual planning assumptions | Strategy | Ava Thompson | 2026-09-21 | 2026-09-27 |  | In Progress |  | A few items still need confirmation.
PPL-26-0146 | Customer: review leave coverage plan | People & Culture | Ethan Brooks | 2026-11-09 | 2026-11-29 |  | Completed |  | Closed after team review.
PPL-26-0147 | FY27: update workplace policy guide | People & Culture | Amelia Wilson | 2026-10-04 | 2026-10-11 |  | Not Started |  | Waiting for the initial briefing.
TEC-26-0148 | FY27: check automated report schedule | Technology | Ava Thompson | 2026-10-18 | 2026-11-07 |  | In Progress |  | Initial review is complete.
STR-26-0149 | Monthly: prepare leadership briefing notes | Strategy | Liam Carter | 2026-10-08 | 2026-11-01 |  | In Progress |  | Work is underway; next update is due shortly.
MKT-26-0150 | FY27: build customer email calendar | Marketing | Oliver Chen | 2026-10-26 | 2026-10-31 |  | In Progress |  | A few items still need confirmation.
OPS-26-0151 | Customer: update stock replenishment guide | Operations | Lucas Brown | 2026-10-24 | 2026-11-05 |  | Completed |  | Deliverable accepted by the relevant lead.
STR-26-0152 | Internal: compare competitor service offers | Strategy | Ava Thompson | 2026-10-11 | 2026-10-15 |  | In Progress |  | Work is underway; next update is due shortly.
OPS-26-0153 | Audit order dispatch records | Operations | Jack Patel | 2026-11-24 | 2026-11-26 |  | In Progress |  | Draft prepared and awaiting feedback.
PPL-26-0154 | Customer: prepare recruitment shortlist | People & Culture | Lucas Brown | 2026-10-12 | 2026-10-21 |  | In Progress |  | Draft prepared and awaiting feedback.
CX-26-0155 | Monthly: review service quality sample | Customer Experience | Jack Patel | 2026-10-30 | 2026-11-11 |  | Not Started |  | Scheduled for the next planning session.
PPL-26-0156 | Phase 2: check employee records | People & Culture | Jack Patel | 2026-10-28 | 2026-11-20 |  | Completed |  | Checks completed; no major issues found.
FIN-26-0157 | Customer: validate purchase order records | Finance | Noah Williams | 2026-10-12 | 2026-10-23 |  | In Progress |  | Progress is being tracked in the team register.
OPS-26-0158 | FY27: coordinate regional delivery schedule | Operations | Priya Shah | 2026-09-15 | 2026-10-03 |  | Completed |  | Closed after team review.
FIN-26-0159 | Monthly: reconcile monthly supplier invoices | Finance | Amelia Wilson | 2026-11-04 | 2026-11-16 |  | Completed |  | Deliverable accepted by the relevant lead.
STR-26-0160 | Phase 2: update annual planning assumptions | Strategy | Amelia Wilson | 2026-10-17 | 2026-11-02 |  | Not Started |  | Scheduled for the next planning session.
PPL-26-0161 | Monthly: review leave coverage plan | People & Culture | Priya Shah | 2026-09-06 | 2026-09-24 |  | In Progress |  | Progress is being tracked in the team register.
OPS-26-0162 | Monthly: document packing quality standards | Operations | Oliver Chen | 2026-10-19 | 2026-10-28 |  | On Hold |  | Paused pending a decision from the project lead.
MKT-26-0163 | FY27: draft customer newsletter | Marketing | Noah Williams | 2026-11-16 | 2026-11-21 |  | Completed |  | Closed after team review.
TEC-26-0164 | Internal: resolve spreadsheet validation issues | Technology | Amelia Wilson | 2026-09-16 | 2026-09-24 |  | In Progress |  | Progress is being tracked in the team register.
CX-26-0165 | Phase 2: refresh help centre articles | Customer Experience | Isabella Martin | 2026-10-02 | 2026-10-19 |  | Completed |  | Checks completed; no major issues found.
MKT-26-0166 | Refresh campaign tracking sheet | Marketing | Ethan Brooks | 2026-10-22 | 2026-11-09 |  | In Progress |  | Follow-up with stakeholders is planned.
TEC-26-0167 | Phase 2: update application support notes | Technology | Isabella Martin | 2026-09-08 | 2026-09-23 |  | In Progress |  | Draft prepared and awaiting feedback.
STR-26-0168 | Internal: prepare leadership briefing notes | Strategy | Lucas Brown | 2026-11-03 | 2026-11-22 |  | In Progress |  | Initial review is complete.
OPS-26-0169 | FY27: audit order dispatch records | Operations | Priya Shah | 2026-09-18 | 2026-10-07 |  | Completed |  | Checks completed; no major issues found.
STR-26-0170 | FY27: compare competitor service offers | Strategy | Isabella Martin | 2026-10-03 | 2026-10-16 |  | On Hold |  | Blocked by an external dependency.
PPL-26-0171 | Monthly: plan quarterly recognition activity | People & Culture | Sophie Taylor | 2026-09-30 | 2026-10-14 |  | In Progress |  | Follow-up with stakeholders is planned.
TEC-26-0172 | Monthly: test reporting dashboard filters | Technology | Noah Williams | 2026-09-06 | 2026-09-10 |  | In Progress |  | Progress is being tracked in the team register.
CX-26-0173 | FY27: identify repeat contact drivers | Customer Experience | Mia Nguyen | 2026-10-29 | 2026-11-09 |  | In Progress |  | A few items still need confirmation.
STR-26-0174 | Monthly: compile market trend summary | Strategy | Liam Carter | 2026-11-16 | 2026-11-27 |  | In Progress |  | Initial review is complete.
PPL-26-0175 | Phase 2: collect induction feedback | People & Culture | Amelia Wilson | 2026-11-02 | 2026-11-22 |  | Not Started |  | Waiting for the initial briefing.
FIN-26-0176 | Customer: validate purchase order records | Finance | Liam Carter | 2026-10-30 | 2026-11-14 |  | In Progress |  | A few items still need confirmation.
TEC-26-0177 | Clean customer data extract | Technology | Ava Thompson | 2026-09-09 | 2026-09-20 |  | In Progress |  | Initial review is complete.
FIN-26-0178 | Customer: review project expenditure | Finance | Priya Shah | 2026-10-03 | 2026-10-13 |  | In Progress |  | Initial review is complete.
TEC-26-0179 | Regional: update application support notes | Technology | Oliver Chen | 2026-11-17 | 2026-11-19 |  | On Hold |  | Blocked by an external dependency.
MKT-26-0180 | Coordinate creative asset review | Marketing | Mia Nguyen | 2026-09-22 | 2026-10-14 |  | In Progress |  | Initial review is complete.